## Closing Schedule
CDG 8/22/24
Directions: Fill in the adoption/execution date and closing date in the blue fields below. All other closing deadline dates will key off of those cells. SAMPLE DATES SHOWN BELOW. | [7 empty] | This is intended to be used as a guide only. Once a closing date has been esbtablished you will receive an offical calendar from a TWDB staff member.
DEADLINE OR MILESTONE | BUSINESS DAYS PRIOR TO ADOPTION | DATE | DAY | Holidays | Blackout Days |  | Closing Date
|  |  |  | 2024-09-02 | 2024-08-26 |  | 2024-11-12
Draft Closing Documents Due | 20 | 2024-09-09 | 1900-01-01 | 2024-11-11 | 2024-08-27 |  | SAFE
Bond Ordinance |  |  |  | 2024-11-27 | 2024-08-28
Paying Agent Agreement |  |  |  | 2024-11-28 | 2024-08-29
Escrow Agreement |  |  |  | 2024-11-29 | 2024-08-30
Private Placement Memorandum |  |  |  | 2024-12-23 | 2024-09-02
Bond Counsel Opinion |  |  |  | 2024-12-24 | 2024-09-03
No Litigation Certificate |  |  |  | 2024-12-25 | 2024-09-04
No Arbitrage/Federal Tax Certificate |  |  |  | 2024-12-26 | 2024-09-05
Disadvantaged Business Enterprise (DBE) Documents Due Contact TWDB DBE Coordinators(SRF EQ Only) | 20 | 2024-09-09 | 1900-01-01 |  | 2024-09-06
Interest Rates for Bond Ordinance from TWDB | 5 | 2024-09-30 | 1900-01-01
TWDB FA sends interest rates |  |  |  | 2025-01-01
|  |  |  | 2025-01-20 | 2024-12-23
Adoption/Execution Date |  | 2024-10-07 | 1900-01-01 |  | 2024-12-24
DEADLINE OR MILESTONE | BUSINESS DAYS AFTER ADOPTION | DATE | DAY
Due to Attorney and Financial Analyst | 3 | 2024-10-10 | 1900-01-04
Executed Agreement Execution Resolution
Executed Principal Forgiveness Escrow Agreement
DEADLINE OR MILESTONE | BUSINESS DAYS PRIOR TO CLOSING | DATE | DAY | 2025-02-17 | 2024-12-25
Water Rights Documentation Due | 45 | 2024-09-09 | 1900-01-01 | 2025-05-26 | 2024-12-26
SRF Equivalency Projects - DBE procurement documents due | 30 | 2024-09-30 | 1900-01-01 |  | 2024-12-27
Release Budget and Supporting Engineering Documents Due to TWDB Engineer | 25 | 2024-10-07 | 1900-01-01 |  | 2024-12-30
Executed Professional Services Contract(s) |  |  |  | 2025-07-04 | 2024-12-31
Sufficiency of Funds Letter (if applicable)
Updated Project Schedule and Updated Budget |  |  |  | 2025-09-01
Updated Project Schedule and Updated Budget |  |  |  |  | 2025-01-01
Financial Advisor's Closing Instruction Memorandum with release amounts (include TWDB Financial Analyst) |  |  |  |  | 2025-01-02
Approved Outlay Report Due to TWDB | 15 | 2024-10-21 | 1900-01-01 |  | 2025-01-03
Final Executed Closing Documents Due to TWDB | 10 | 2024-10-28 | 1900-01-01
Bond Ordinance or Resolution adopting the issuance
Debt Service Schedule
Executed Escrow Agreement
Financial Advisor’s Closing Instruction Memorandum
Executed Paying Agent Agreement
Private Placement Memorandum – with all attachments
TWDB Vendor Set-Up or Direct Deposit Form
Blanket Issuer Letter of Representations (BLOR)
Bond Counsel Opinion
No Litigation Certificate
No Arbitrage/Federal Tax Certificate
FMT Letter (Drinking Water Funding Only)
Executed Loan Forgiveness Agreement {Only if applicant also receiving loan forgiveness}
Comptroller’s Certificate (5 business days prior) | 5 | 2024-11-04 | 1900-01-01
Attorney General Opinion (5 business days prior)
Revisions to closing documents, if needed | 4
3
2
1
Closing Date |  | 2024-11-12 | 1900-01-02
*Milestones in yellow are hard deadlines. Failure to meet deadlines will likely result in a rescheduled closing date*
Formulas:
DATE = WORKDAY.INTL(D19,-[BUSINESS DAYS PRIOR TO ADOPTION],,holidays)
DATE = WORKDAY.INTL(D19,[BUSINESS DAYS PRIOR TO ADOPTION],,holidays)
DAY = WEEKDAY([DATE])