## Services
Floodville FMA 22 C&CB Project Scoping Budget
Task | Description | Cost Category | Senior Engineer | Project Manager | Grant Manager | Engineer | GIS | Admin | Total Hours | Total Cost
1 Project Management
a | Project Management | Contractual | 42 |  |  | 50 |  | 5 | 97 | 15975
b | Grant Management | Personel |  |  | 60 |  |  |  | 60 | 9000
c | Grant Management | Contractual | 15 |  |  | 5 |  |  | 20 | 4250
[9 empty] | Sub-total: | 29225
2 Data Collection
a | Collect Exisiting Data | Contractual | 6 | 50 |  | 40 |  |  | 96 | 17000
b | Collect Terrain Data | Contractual | 4 | 20 |  | 40 |  |  | 64 | 9600
c | Survey | Contractual | 87 | 6 |  | 40 | 30 |  | 163 | 29980
d | QA/QC | Contractual | 5 | 7 |  | 30 |  |  | 42 | 5860
[9 empty] | Sub-total: | 62440
3 Hydrologic and Hydraulic analysis
a | Hydrologic Analysis | Contractual |  | 25 |  | 40 |  |  | 65 | 9750
b | Hydraulic Analysis | Contractual | 42 | 35 |  | 40 |  |  | 117 | 22550
c | Model Development | Contractual | 10 | 4 |  | 40 |  |  | 54 | 7420
d | Technical Memo | Contractual | 7 | 12 |  | 40 |  | 5 | 64 | 8985
e | QA/QC | Contractual |  | 18 |  | 30 |  |  | 48 | 7140
[9 empty] | Sub-total: | 55845
4 Flood Mitigation Alternatives Identification
a | Identify Flood Risk area | Contractual | 20 | 80 |  | 40 |  |  | 140 | 27400
b | Mitigation Alternative Recommendation | Contractual | 53 | 45 |  | 40 |  |  | 138 | 27600
c | Draft Recommendation Technical Memo | Contractual | 7 | 60 |  | 40 |  | 5 | 112 | 20025
d | QA/QC | Contractual |  | 46 |  | 20 |  |  | 66 | 12580
[9 empty] | Sub-total: | 87605
5 Project Delivery
a | Draft Report | Contractual | 12 | 30 |  | 30 |  | 5 | 77 | 13375
b | Final Report | Contractual | 12 | 30 |  | 30 |  | 5 | 77 | 13375
c | Model Delivery | Contractual | 8 |  |  | 16 |  | 5 | 29 | 4075
[9 empty] | Sub-total: | 30825
| Total Hours: |  | 330 | 468 | 60 | 611 | 30 | 30 | 1529
| Labor Rate |  | 250 | 230 | 150 | 100 | 95 | 95
| Total Amount |  | 82500 | 107640 | 9000 | 61100 | 2850 | 2850 |  | 265940
Note on C2: Cody Ransone: Refer to detailed definitions on SF-424A instructions on GRANTS.gov for more information on Cost Categories.