## WorkbookDataTabDescriptions
Workbook Description: This workbook contains 2022 State Water Plan recommended water management strategy project (WMSP) data to be used for the WMS project feasibility review task. Data queried on 12/21/2022 and filtered by WMS project sponsor region = 'I'. Recommended WMS are listed in the Excel workbook titled '2022SWPWMS&ProjectFeasibilityAnalysis_WMSWorkbook.' To see strategy details such as WUG geographic information or source geographic information and WMS/WMS project relationships see the Excel workbook titled '2022SWPWMS&ProjectFeasibilityAnalysis_WMSDetails&ProjectRelationships.'
Workbook Tab Name | Workbook tab description
2020WMSProjects | Tab contains projects with an online decade of 2020. This tab is required to be assessed.
SelectProjectsOnlineAfter2020 | Tab contains WMS projects that have an online planning decade of 2030 or 2040 and -Direct potable reuse strategies that provide greater than 5,000 acre-feet per year (acre-feet/year) of supply in any planning decade -Brackish groundwater strategies that provide greater than 10,000 acre-feet/year of supply in any planning decade -Aquifer storage and recovery strategies that provide greater than 10,000 acre-feet/year in any decade -All water transfers from out of state or WMS projects related to new major reservoirs or seawater desalination that occur in any planning decade after 2020.

## 2020WMSProjects
Tab 1: Recommended WMS projects associated with an online decade of 2020
WMS Project identified as infeasible? (Y/N) | RWPG Comments | Project Sponsor Region | Project Category | WMS Project Id | WMS Project Name | Capital Cost | Online Decade | Project Sponsors | Project Components | Project Related WMS Types | Project Related Source Subtypes | Project Related Strategy Supply 2020 AFY | Project Related Strategy Supply 2030 AFY | Project Related Strategy Supply 2040 AFY | Project Related Strategy Supply 2050 AFY | Project Related Strategy Supply 2060 AFY | Project Related Strategy Supply 2070 AFY
|  | I | Other project type | 3926 | CHER-ALT-New Wells in Carrizo-Wilcox Aquifer | 2426000 | 2020 | Alto Rural WSC | Conveyance/Transmission Pipeline; Multiple Wells/Well Field; Pump Station; Storage Tank | Groundwater wells and other | Groundwater | 0 | 0 | 0 | 191 | 191 | 191
|  | I | Other project type | 4410 | HDSN-ATN-Advanced Conservation | 786000 | 2020 | Athens | Conservation - Municipal (does not include meter replacement or water loss); Data Gathering/Monitoring Technology; Water Loss Control | Municipal conservation |  | 7 | 13 | 16 | 20 | 23 | 27
|  | I | Other project type | 4411 | JEFF-BEA-Advanced Conservation | 60175000 | 2020 | Beaumont | Conservation - Municipal (does not include meter replacement or water loss); Data Gathering/Monitoring Technology; Water Loss Control | Municipal conservation |  | 2027 | 3425 | 4202 | 5112 | 6171 | 7382
|  | I | New major reservoir | 2009 | LNVA-WRR-Beaumont West Regional Reservoir | 37538000 | 2020 | Lower Neches Valley Authority | Pump Station; Reservoir Construction | New major reservoir | Reservoir | 0 | 7700 | 7700 | 7700 | 7700 | 7700
|  | I | Other project type | 3959 | PORT-CONS-City of Port Arthur - Advanced Conservation | 51618000 | 2020 | Port Arthur | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 2708 | 4449 | 5222 | 6029 | 6844 | 7664
|  | I | Other project type | 2056 | RUSK-MIN-Purchase from Angelina Neches River Authority (Angelina River) | 14808000 | 2020 | Mining (Rusk) | Conveyance/Transmission Pipeline; Pump Station; Storage Tank | Other surface water | Run-of-River | 0 | 305 | 168 | 22 | 0 | 0
|  | I | Other project type | 2050 | SHEL-LTK-Purchase from Sabine River Authority (Toledo Bend) | 18582000 | 2020 | Livestock (Shelby) | Conveyance/Transmission Pipeline; Pump Station; Storage Tank | Other surface water | Reservoir | 6491 | 8761 | 11524 | 14896 | 19006 | 19006
|  | I | Other project type | 3962 | SHEL-SHW-Purchase from Center | 102000 | 2020 | Sand Hills WSC | New Contract; Conveyance/Transmission Pipeline | Other surface water | Reservoir | 61 | 68 | 77 | 87 | 97 | 105
|  | I | Other project type | 2045 | SMTH-CYS-New Wells in Carrizo-Wilcox Aquifer | 2531000 | 2020 | Crystal Systems Texas | Conveyance/Transmission Pipeline; Pump Station; Storage Tank | Groundwater wells and other | Groundwater | 0 | 0 | 135 | 135 | 269 | 538
|  | I | Other project type | 2047 | SMTH-LDL-Infrastructure | 7592000 | 2020 | Lindale | Conveyance/Transmission Pipeline; Pump Station; Storage Tank | Other surface water | Reservoir | 0 | 180 | 323 | 490 | 662 | 826
|  | I | Other project type | 2048 | SMTH-MFG-Purchase from City of Tyler | 6198000 | 2020 | Manufacturing (Smith) | Conveyance/Transmission Pipeline; Pump Station; Storage Tank | Other surface water | Reservoir | 0 | 84 | 84 | 84 | 84 | 84
|  | I | Other project type | 2149 | UNM-LP-Run of River, Neches with Lake Palestine | 518977000 | 2020 | Upper Neches River Municipal Water Authority | Conveyance/Transmission Pipeline; Pump Station; Storage Tank | Other surface water | Run-of-River | 68625 | 68625 | 68625 | 68625 | 68625 | 68625
|  | I | Other project type | 3950 | WUG-CONS-Municipal Conservation- Crystal Systems Texas | 954000 | 2020 | Crystal Systems Texas | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 18 | 38 | 52 | 71 | 92 | 118
|  | I | Other project type | 3952 | WUG-CONS-Municipal Conservation- Henderson | 9900000 | 2020 | Henderson | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 83 | 148 | 179 | 235 | 283 | 334
|  | I | Other project type | 3954 | WUG-CONS-Municipal Conservation- Nacogdoches | 27720000 | 2020 | Nacogdoches | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 247 | 426 | 532 | 656 | 802 | 966
|  | I | Other project type | 3951 | WUG-CONS-Municipal Conservation-Cushing | 1030000 | 2020 | Cushing | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 10 | 19 | 24 | 30 | 37 | 45
|  | I | Other project type | 3953 | WUG-CONS-Municipal Conservation-Jasper | 15444000 | 2020 | Jasper | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 75 | 124 | 141 | 158 | 178 | 196
|  | I | Other project type | 3955 | WUG-CONS-Municipal Conservation-San Augustine | 2297000 | 2020 | San Augustine | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 10 | 17 | 18 | 20 | 22 | 23
|  | I | Other project type | 3956 | WUG-CONS-Municipal Conservation-Southern Utilities | 33264000 | 2020 | Southern Utilities | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 514 | 866 | 1058 | 1279 | 1527 | 1803
|  | I | Other project type | 3957 | WUG-CONS-Municipal Conservation-Tyler | 58766000 | 2020 | Tyler | Conservation - Municipal (does not include meter replacement or water loss) | Municipal conservation |  | 657 | 1101 | 1338 | 1613 | 1924 | 2268

## SelectProjectsOnlineAfter2020
Tab 2: Select Recommended WMS projects associated with an online decade of later than 2020. See workbook data description tab for details about selected projects.
WMS Project identified as infeasible? (Y/N) | RWPG Comments | Project Sponsor Region | Project Category | WMS Project Id | WMS Project Name | Capital Cost | Online Decade | Project Sponsors | Project Components | Project Related WMS Types | Project Related Source Subtypes | Project Related Strategy Supply 2020 AFY | Project Related Strategy Supply 2030 AFY | Project Related Strategy Supply 2040 AFY | Project Related Strategy Supply 2050 AFY | Project Related Strategy Supply 2060 AFY | Project Related Strategy Supply 2070 AFY
|  | I | New major reservoir | 1696 | ANRA-COL-Lake Columbia | 402862000 | 2030 | Angelina and Neches River Authority | Reservoir Construction | New major reservoir | Reservoir | 0 | 75550 | 75500 | 75450 | 75400 | 75350