## PrioritizationList+Ids
Sponsor | Recommended Water Management Strategy | CapitalCost | Supply 2010 | Supply 2020 | Supply 2030 | Supply 2040 | Supply 2050 | Supply 2060 | Project Description | Infrastructure Type* | At what level of Implementation is the project?* | If not implemented, why?* | Initial Volume of Water Provided (acft/yr) | Funds Expended to Date ($) | Project Cost ($) (should include development and construction costs) | Year the Project is Online?* | Is this a phased project?* | (Phased) Ultimate Volume (acft/yr) | (Phased) Ultimate Project Cost ($) | Year project reaches maximum capacity?* | What is the project funding source(s)?* | Included in the 2016 Plan?* | Comments
ALAMO HEIGHTS | Drought management | 0 | 104 | 0 | 0 | 0 | 0 | 0
ALAMO HEIGHTS | Edwards transfers | 0 | 592 | 655 | 657 | 653 | 667 | 691
ALAMO HEIGHTS | Municipal water conservation | 0 | 175 | 337 | 488 | 625 | 769 | 865
AQUA WSC | Drought management | 0 | 13 | 0 | 0 | 0 | 0 | 0
AQUA WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 1984000 | 403 | 403 | 403 | 403 | 403 | 403
AQUA WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 6 | 19
ASHERTON | Municipal water conservation | 0 | 20 | 43 | 58 | 59 | 62 | 64
ATASCOSA RURAL WSC | Drought management | 0 | 47 | 0 | 0 | 0 | 0 | 0
ATASCOSA RURAL WSC | Edwards transfers | 0 | 546 | 717 | 869 | 996 | 1106 | 1218
ATASCOSA RURAL WSC | Facilities expansion | 72433000 | 0 | 0 | 0 | 0 | 0 | 0
ATASCOSA RURAL WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 0 | 120 | 120 | 120 | 120 | 120 | 120
ATASCOSA RURAL WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 22
BALCONES HEIGHTS | Municipal water conservation | 0 | 4 | 6 | 7 | 9 | 20 | 37
BENTON CITY WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 4372000 | 0 | 0 | 807 | 807 | 807 | 1613
BENTON CITY WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 24 | 85 | 153
BEXAR MET WATER DISTRICT | CRWA Wells Ranch project Phase I | 0 | 2800 | 5200 | 5200 | 5200 | 5200 | 5200 |  |  | Currently Operating |  | 2,800 acft/yr |  |  | 2012 | [5 empty] | Yes | CRWA Project- SAWS contract for 2,800 acft/yr
BEXAR MET WATER DISTRICT | CRWA Wells Ranch project Phase II (including Gonzales County) | 0 | 0 | 3050 | 3050 | 3050 | 3050 | 3050 | [13 empty] | No | SAWS not participating in Wells Ranch Phase II
BEXAR MET WATER DISTRICT | Edwards transfers | 0 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | [13 empty] | No | See San Antonio Water System
BEXAR MET WATER DISTRICT | Local groundwater (Trinity Aquifer) | 9662000 | 2016 | 2016 | 2016 | 2016 | 2016 | 2016 | [13 empty] | No | Not implemented
BEXAR MET WATER DISTRICT | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 44372000 | 4030 | 6448 | 8060 | 8060 | 12090 | 16129 | [13 empty] | No | Not implemented
BEXAR MET WATER DISTRICT | Medina Lake firm-up (aquifer storage and recovery) | 146237000 | 9933 | 9933 | 9933 | 9933 | 9933 | 9933 | [13 empty] | No | Project not being implemented
BEXAR MET WATER DISTRICT | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 293 | [13 empty] | Yes | See San Antonio Water System
BIG WELLS | Municipal water conservation | 0 | 11 | 23 | 30 | 30 | 32 | 33
BOERNE | Municipal water conservation | 0 | 98 | 280 | 394 | 502 | 652 | 816
BOERNE | Western Canyon water treatment plant expansion | 0 | 0 | 0 | 0 | 0 | 0 | 276
BULVERDE CITY | Drought management | 0 | 53 | 0 | 0 | 0 | 0 | 0
BULVERDE CITY | GBRA Simsboro project (overdraft) | 0 | 0 | 1342 | 2128 | 2910 | 3723 | 4595
BULVERDE CITY | Municipal water conservation | 0 | 0 | 0 | 38 | 130 | 260 | 430
BULVERDE CITY | Purchase from wholesale water provider (GBRA) | 0 | 653 | 0 | 0 | 0 | 0 | 0
BULVERDE CITY | TWA Regional Carrizo (including Gonzales County) | 0 | 0 | 1342 | 2128 | 2910 | 3723 | 4595
CANYON LAKE WSC | GBRA Simsboro project (overdraft) | 0 | 0 | 0 | 129 | 2198 | 4466 | 6769
CANYON LAKE WSC | Municipal water conservation | 0 | 0 | 96 | 254 | 543 | 929 | 1414
CANYON LAKE WSC | TWA Regional Carrizo (including Gonzales County) | 0 | 0 | 0 | 3000 | 6000 | 9000 | 12000
CANYON REGIONAL WATER AUTHORITY | Brackish groundwater desalination (Wilcox Aquifer) | 97347786 | 0 | 0 | 5600 | 5600 | 11200 | 11200
CANYON REGIONAL WATER AUTHORITY | CRWA Siesta project | 53481000 | 0 | 0 | 1000 | 5042 | 5042 | 5042
CANYON REGIONAL WATER AUTHORITY | CRWA Wells Ranch project Phase I | 0 | 5200 | 5200 | 5200 | 5200 | 5200 | 5200
CANYON REGIONAL WATER AUTHORITY | CRWA Wells Ranch project Phase II (including Gonzales County) | 34910000 | 5800 | 5800 | 5800 | 5800 | 5800 | 5800
CANYON REGIONAL WATER AUTHORITY | GBRA mid basin (surface water) | 0 | 0 | 5000 | 5000 | 5000 | 5000 | 5000
CANYON REGIONAL WATER AUTHORITY | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 94758058 | 0 | 5000 | 10260 | 10260 | 10260 | 10260
CARRIZO SPRINGS | Municipal water conservation | 0 | 152 | 312 | 464 | 590 | 700 | 777
CASTLE HILLS | Drought management | 0 | 41 | 0 | 0 | 0 | 0 | 0
CASTLE HILLS | Local groundwater (Trinity Aquifer) | 0 | 96 | 83 | 69 | 56 | 47 | 47
CASTLE HILLS | Municipal water conservation | 0 | 61 | 120 | 142 | 144 | 151 | 166
CASTROVILLE | Drought management | 0 | 34 | 0 | 0 | 0 | 0 | 0
CASTROVILLE | Edwards transfers | 0 | 294 | 357 | 416 | 468 | 522 | 575
CASTROVILLE | Facilities expansion | 11046000 | 0 | 0 | 0 | 0 | 0 | 0
CASTROVILLE | Municipal water conservation | 0 | 53 | 111 | 176 | 242 | 270 | 302
CHARLOTTE | Drought management | 0 | 15 | 0 | 0 | 0 | 0 | 0
CHARLOTTE | Facilities expansion | 38356000 | 0 | 0 | 0 | 0 | 0 | 0
CHARLOTTE | Municipal water conservation | 0 | 20 | 23 | 25 | 26 | 34 | 43
CHINA GROVE | Municipal water conservation | 0 | 28 | 66 | 116 | 166 | 190 | 217
CIBOLO | CRWA Siesta project | 0 | 0 | 0 | 0 | 0 | 326 | 326
CIBOLO | CRWA Wells Ranch project Phase I | 0 | 700 | 0 | 0 | 0 | 0 | 0
CIBOLO | CRWA Wells Ranch project Phase II (including Gonzales County) | 0 | 0 | 980 | 2054 | 1854 | 1854 | 1854
CIBOLO | GBRA mid basin (surface water) | 0 | 0 | 0 | 4126 | 4826 | 5000 | 5000
CIBOLO | Medina Lake firm-up (aquifer storage and recovery) | 0 | 500 | 500 | 500 | 500 | 500 | 500
CIBOLO | Municipal water conservation | 0 | 65 | 176 | 281 | 374 | 499 | 645
CONVERSE | Local groundwater (Trinity Aquifer) | 0 | 0 | 0 | 134 | 449 | 716 | 969
CONVERSE | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 21 | 110
COTULLA | Municipal water conservation | 0 | 118 | 248 | 369 | 488 | 615 | 745
COUNTY LINE WSC | Drought management | 0 | 58 | 0 | 0 | 0 | 0 | 0
COUNTY LINE WSC | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 570 | 570 | 570 | 570 | 570
COUNTY LINE WSC | Local groundwater (Trinity Aquifer) | 20562000 | 0 | 1129 | 1452 | 1613 | 1936 | 2420
COUNTY LINE WSC | Municipal water conservation | 0 | 43 | 110 | 176 | 227 | 344 | 473
COUNTY-OTHER, ATASCOSA | Municipal water conservation | 0 | 11 | 17 | 11 | 1 | 0 | 0
COUNTY-OTHER, BEXAR | Edwards transfers | 0 | 0 | 0 | 0 | 127 | 403 | 655
COUNTY-OTHER, BEXAR | Municipal water conservation | 0 | 49 | 96 | 140 | 191 | 310 | 505
COUNTY-OTHER, CALDWELL | Facilities expansion | 17584000 | 0 | 0 | 0 | 0 | 0 | 0
COUNTY-OTHER, CALDWELL | Municipal water conservation | 0 | 21 | 37 | 36 | 31 | 28 | 29
COUNTY-OTHER, COMAL | GBRA Simsboro project (overdraft) | 0 | 0 | 986 | 1089 | 1181 | 1333 | 1480
COUNTY-OTHER, COMAL | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 85
COUNTY-OTHER, COMAL | Purchase from New Braunfels Utilities/redistribution of supplies | 0 | 891 | 0 | 0 | 0 | 0 | 0
COUNTY-OTHER, COMAL | Purchase from wholesale water provider (GBRA) | 0 | 891 | 0 | 0 | 0 | 0 | 0
COUNTY-OTHER, COMAL | TWA Regional Carrizo (including Gonzales County) | 0 | 0 | 986 | 1089 | 1181 | 1333 | 1480
COUNTY-OTHER, DEWITT | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 6
COUNTY-OTHER, FRIO | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 18
COUNTY-OTHER, GOLIAD | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 16
COUNTY-OTHER, GONZALES | Municipal water conservation | 0 | 6 | 7 | 5 | 0 | 0 | 3
COUNTY-OTHER, GUADALUPE | Municipal water conservation | 0 | 2 | 0 | 0 | 0 | 0 | 0
COUNTY-OTHER, HAYS | Municipal water conservation | 0 | 0 | 0 | 12 | 49 | 112 | 184
COUNTY-OTHER, KARNES | Municipal water conservation | 0 | 68 | 121 | 157 | 193 | 227 | 258
COUNTY-OTHER, KENDALL | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 73 | 264
COUNTY-OTHER, KENDALL | Purchase from wholesale water provider (GBRA) | 0 | 221 | 0 | 0 | 0 | 0 | 0
COUNTY-OTHER, KENDALL | Storage above Canyon Reservoir (aquifer storage and recovery) | 0 | 0 | 3140 | 3140 | 3140 | 3140 | 3140
COUNTY-OTHER, KENDALL | Western Canyon water treatment plant expansion | 0 | 0 | 0 | 0 | 0 | 0 | 374
COUNTY-OTHER, LA SALLE | Municipal water conservation | 0 | 3 | 4 | 11 | 17 | 29 | 42
COUNTY-OTHER, MEDINA | Edwards transfers | 0 | 0 | 236 | 528 | 787 | 1055 | 1296
COUNTY-OTHER, MEDINA | Municipal water conservation | 0 | 0 | 20 | 41 | 86 | 160 | 244
COUNTY-OTHER, UVALDE | Municipal water conservation | 0 | 0 | 0 | 0 | 33 | 73 | 137
COUNTY-OTHER, VICTORIA | GBRA new appropriation (lower basin) | 0 | 0 | 0 | 0 | 81 | 193 | 310
COUNTY-OTHER, VICTORIA | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 32
COUNTY-OTHER, WILSON | Municipal water conservation | 0 | 0 | 0 | 0 | 14 | 58 | 116
COUNTY-OTHER, ZAVALA | Municipal water conservation | 0 | 42 | 54 | 71 | 89 | 115 | 149
CREEDMOOR-MAHA WSC | GBRA mid basin (surface water) | 0 | 0 | 180 | 246 | 312 | 378 | 447
CREEDMOOR-MAHA WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 11
CREEDMOOR-MAHA WSC | Purchase from wholesale water provider (GBRA) | 0 | 108 | 0 | 0 | 0 | 0 | 0
CRYSTAL CITY | Municipal water conservation | 0 | 192 | 364 | 543 | 695 | 850 | 1002
CRYSTAL CLEAR WSC | Brackish groundwater desalination (Wilcox Aquifer) | 0 | 0 | 0 | 596 | 596 | 3184 | 3184
CRYSTAL CLEAR WSC | CRWA Wells Ranch project Phase I | 0 | 1300 | 0 | 0 | 0 | 0 | 0
CRYSTAL CLEAR WSC | GBRA mid basin (surface water) | 0 | 0 | 2595 | 0 | 0 | 0 | 0
CRYSTAL CLEAR WSC | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 0 | 2000 | 2000 | 2000 | 2000
CRYSTAL CLEAR WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 33754000 | 0 | 0 | 605 | 1210 | 2016 | 2823
CRYSTAL CLEAR WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 41 | 184
CRYSTAL CLEAR WSC | Regional Carrizo for SSLGC project expansion (including Gonzales County) | 0 | 0 | 300 | 600 | 900 | 900 | 900
CUERO | Municipal water conservation | 0 | 99 | 181 | 187 | 190 | 197 | 218
DEVINE | Municipal water conservation | 0 | 63 | 127 | 152 | 159 | 175 | 196
DILLEY | Municipal water conservation | 0 | 104 | 229 | 362 | 511 | 652 | 772
EAST CENTRAL WSC | Edwards transfers | 0 | 2240 | 2240 | 2240 | 2240 | 2240 | 2240
EAST CENTRAL WSC | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 0 | 251 | 495 | 716 | 942
EAST CENTRAL WSC | Local groundwater (Trinity Aquifer) | 0 | 200 | 200 | 200 | 200 | 200 | 200
EAST CENTRAL WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 32 | 104
EAST MEDINA SUD | Drought management | 0 | 44 | 0 | 0 | 0 | 0 | 0
EAST MEDINA SUD | Edwards transfers | 0 | 0 | 104 | 214 | 303 | 397 | 491
EAST MEDINA SUD | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 19 | 54
EL OSO WSC | Municipal water conservation | 0 | 41 | 83 | 92 | 105 | 120 | 139
ELMENDORF | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 2 | 6
ENCINAL | Municipal water conservation | 0 | 9 | 9 | 10 | 10 | 11 | 14
FAIROAKS RANCH | Municipal water conservation | 0 | 125 | 246 | 358 | 460 | 481 | 509
FALLS CITY | Municipal water conservation | 0 | 8 | 13 | 14 | 16 | 19 | 23
FLORESVILLE | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 2344000 | 0 | 0 | 0 | 0 | 484 | 484
FLORESVILLE | Municipal water conservation | 0 | 136 | 291 | 433 | 504 | 596 | 714
GARDEN RIDGE | Drought management | 0 | 28 | 0 | 0 | 0 | 0 | 0
GARDEN RIDGE | Municipal water conservation | 0 | 42 | 104 | 188 | 294 | 380 | 460
GARDEN RIDGE | Purchase from wholesale water provider (SSLGC)/redistribution of supplies | 0 | 257 | 395 | 552 | 710 | 873 | 1052
GOFORTH WSC | GBRA mid basin (surface water) | 0 | 0 | 0 | 300 | 300 | 300 | 300
GOFORTH WSC | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 15139490 | 0 | 1639 | 1639 | 1639 | 1639 | 1639 | Carrizo groundwater project | Other | Acquisition and Design Phase | Too soon | 15000 | 10500000 |  |  | Yes | 35690 | 400000000 | 2060 | Self (cash) | Yes | Goforth WSC has not contracted with the Hays Caldwell PUA for water supply.
GOFORTH WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 22 | 111
GOLIAD | Municipal water conservation | 0 | 30 | 59 | 67 | 73 | 85 | 100
GONZALES | Municipal water conservation | 0 | 116 | 245 | 325 | 353 | 381 | 414
GONZALES COUNTY WSC | Municipal water conservation | 0 | 143 | 312 | 505 | 693 | 858 | 1002
GONZALES COUNTY WSC | TWA Regional Carrizo (including Gonzales County) | 0 | 0 | 500 | 500 | 500 | 500 | 500
GREEN VALLEY SUD | Brackish groundwater desalination (Wilcox Aquifer) | 0 | 0 | 0 | 3000 | 3000 | 6012 | 6012
GREEN VALLEY SUD | CRWA Siesta project | 0 | 0 | 0 | 1000 | 4995 | 2985 | 3485
GREEN VALLEY SUD | CRWA Wells Ranch project Phase II (including Gonzales County) | 0 | 700 | 0 | 0 | 0 | 0 | 0
GREEN VALLEY SUD | GBRA mid basin (surface water) | 0 | 0 | 1800 | 0 | 0 | 0 | 0
GREEN VALLEY SUD | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 0 | 3500 | 0 | 0 | 0
GREEN VALLEY SUD | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 20
GREEN VALLEY SUD | Purchase from New Braunfels Utilities/redistribution of supplies | 0 | 552 | 552 | 552 | 552 | 552 | 552
GUADALUPE BLANCO RIVER AUTHORITY | GBRA Exelon project | 280598000 | 0 | 49126 | 49126 | 49126 | 49126 | 49126
GUADALUPE BLANCO RIVER AUTHORITY | GBRA Integrated Water Power Project | 1282426000 | 0 | 100000 | 100000 | 100000 | 100000 | 100000
GUADALUPE BLANCO RIVER AUTHORITY | GBRA lower basin storage | 33800000 | 0 | 0 | 28369 | 28369 | 28369 | 28369
GUADALUPE BLANCO RIVER AUTHORITY | GBRA mid basin (surface water) | 546941000 | 0 | 25000 | 25000 | 25000 | 25000 | 25000
GUADALUPE BLANCO RIVER AUTHORITY | GBRA new appropriation (lower basin) | 246849000 | 0 | 0 | 11300 | 11300 | 11300 | 11300
GUADALUPE BLANCO RIVER AUTHORITY | GBRA Simsboro project (overdraft) | 330782000 | 0 | 30000 | 30000 | 30000 | 49777 | 49777
GUADALUPE BLANCO RIVER AUTHORITY | Storage above Canyon Reservoir (aquifer storage and recovery) | 37326000 | 0 | 3140 | 3140 | 3140 | 3140 | 3140
GUADALUPE BLANCO RIVER AUTHORITY | Western Canyon water treatment plant expansion | 11727436 | 0 | 0 | 0 | 0 | 5600 | 5600
GUADALUPE BLANCO RIVER AUTHORITY | Wimberley and Woodcreek water supply project | 33771000 | 1120 | 4480 | 4480 | 4480 | 4480 | 4480
HELOTES | Facilities expansion | 2863000 | 0 | 0 | 0 | 0 | 0 | 0
HELOTES | Municipal water conservation | 0 | 115 | 345 | 539 | 674 | 832 | 993
HILL COUNTRY VILLAGE | Drought management | 0 | 42 | 0 | 0 | 0 | 0 | 0
HILL COUNTRY VILLAGE | Edwards transfers | 0 | 730 | 727 | 723 | 720 | 718 | 718
HILL COUNTRY VILLAGE | Municipal water conservation | 0 | 77 | 146 | 209 | 265 | 316 | 365
HOLLYWOOD PARK | Drought management | 0 | 116 | 0 | 0 | 0 | 0 | 0
HOLLYWOOD PARK | Edwards transfers | 0 | 1969 | 2044 | 2113 | 2166 | 2220 | 2271
HOLLYWOOD PARK | Municipal water conservation | 0 | 212 | 414 | 612 | 798 | 980 | 1154
HONDO | Drought management | 0 | 89 | 0 | 0 | 0 | 0 | 0
HONDO | Edwards transfers | 0 | 319 | 536 | 740 | 910 | 1083 | 1252
HONDO | Municipal water conservation | 0 | 125 | 289 | 420 | 477 | 551 | 640
IRRIGATION, ATASCOSA | Irrigation water conservation | 0 | 5369 | 4734 | 3413 | 2141 | 924 | 290
IRRIGATION, MEDINA | Irrigation water conservation | 0 | 7770 | 5879 | 4068 | 2332 | 671 | 0
IRRIGATION, ZAVALA | Irrigation water conservation | 0 | 6948 | 6948 | 6948 | 6948 | 6948 | 6948
JOURDANTON | Drought management | 0 | 40 | 0 | 0 | 0 | 0 | 0
JOURDANTON | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 2441000 | 403 | 403 | 403 | 403 | 403 | 403
JOURDANTON | Municipal water conservation | 0 | 60 | 123 | 156 | 173 | 195 | 222
KARNES CITY | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 3430000 | 323 | 323 | 323 | 323 | 323 | 323
KARNES CITY | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 11
KENEDY | Local groundwater (Gulf Coast Aquifer) | 2194000 | 0 | 0 | 0 | 161 | 161 | 161
KENEDY | Municipal water conservation | 0 | 58 | 121 | 189 | 216 | 242 | 268
KIRBY | Drought management | 0 | 50 | 0 | 0 | 0 | 0 | 0
KIRBY | Edwards transfers | 0 | 335 | 334 | 337 | 331 | 343 | 364
KYLE | Drought management | 0 | 137 | 0 | 0 | 0 | 0 | 0
KYLE | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 86417021 | 0 | 500 | 1000 | 2416 | 5144 | 9355 | Carrizo groundwater project | Other | Acquisition and Design Phase | Too soon | 15000 | 10500000 |  |  | Yes | 35690 | 400000000 | 2060 | Self (cash) | Yes | Project will consist of wells, a treatment plant & pipelines. Anticipate issuing first debt for construction late in 2015.
KYLE | Municipal water conservation | 0 | 0 | 27 | 96 | 167 | 302 | 443
LA VERNIA | CRWA Wells Ranch project Phase I | 0 | 400 | 0 | 0 | 0 | 0 | 0
LA VERNIA | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 400 | 400 | 400 | 400 | 400
LA VERNIA | Municipal water conservation | 0 | 21 | 56 | 105 | 146 | 184 | 227
LACKLAND AFB | Municipal water conservation | 0 | 268 | 515 | 736 | 934 | 1119 | 1300
LACOSTE | Drought management | 0 | 10 | 0 | 0 | 0 | 0 | 0
LACOSTE | Edwards transfers | 0 | 92 | 109 | 126 | 138 | 152 | 168
LACOSTE | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 4 | 11
LEON VALLEY | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 12
LIVESTOCK, GOLIAD | Livestock water conservation | 0 | 3 | 1 | 0 | 0 | 0 | 0
LOCKHART | Drought management | 0 | 123 | 0 | 0 | 0 | 0 | 0
LOCKHART | GBRA mid basin (surface water) | 0 | 0 | 1120 | 1120 | 1120 | 1120 | 1120
LOCKHART | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 24246000 | 0 | 403 | 1210 | 1613 | 2016 | 2823
LOCKHART | Municipal water conservation | 0 | 0 | 0 | 28 | 103 | 195 | 333
LULING | Drought management | 0 | 53 | 0 | 0 | 0 | 0 | 0
LULING | GBRA mid basin (surface water) | 0 | 0 | 1680 | 1680 | 1680 | 1680 | 1680
LULING | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 5906000 | 0 | 403 | 403 | 403 | 403 | 807
LULING | Municipal water conservation | 0 | 70 | 90 | 108 | 117 | 148 | 192
LYTLE | Drought management | 0 | 24 | 0 | 0 | 0 | 0 | 0
LYTLE | Edwards transfers | 0 | 141 | 152 | 162 | 169 | 179 | 188
LYTLE | Municipal water conservation | 0 | 38 | 72 | 82 | 86 | 96 | 108
MANUFACTURING, BEXAR | Edwards transfers | 0 | 0 | 873 | 2873 | 6873 | 14873 | 14873
MANUFACTURING, BEXAR | Recycled water programs | 196094169 | 1340 | 4886 | 8240 | 11537 | 14438 | 17588
MANUFACTURING, BEXAR | Recycled water programs | 0 | 4240 | 7367 | 15127 | 15127 | 15127 | 15127
MANUFACTURING, CALHOUN | Construction of Lavaca River off-channel reservoir diversion project (Region L component) | 85429083 | 0 | 10000 | 10000 | 10000 | 10000 | 10000
MANUFACTURING, COMAL | GBRA Simsboro project (overdraft) | 0 | 0 | 6033 | 6784 | 7514 | 8141 | 9022
MANUFACTURING, COMAL | Purchase from wholesale water provider (GBRA) | 0 | 5199 | 0 | 0 | 0 | 0 | 0
MANUFACTURING, COMAL | Recycled water programs | 100589128 | 5199 | 6033 | 6784 | 7514 | 8141 | 9022
MANUFACTURING, VICTORIA | GBRA lower basin storage | 0 | 0 | 0 | 5921 | 8860 | 11489 | 14441
MANUFACTURING, VICTORIA | Purchase from wholesale water provider (GBRA) | 0 | 0 | 2969 | 0 | 0 | 0 | 0
MARION | CRWA Siesta project | 0 | 0 | 0 | 0 | 47 | 400 | 400
MARION | CRWA Wells Ranch project Phase II (including Gonzales County) | 0 | 100 | 200 | 0 | 0 | 0 | 0
MARION | GBRA mid basin (surface water) | 0 | 0 | 0 | 400 | 174 | 0 | 0
MARION | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 0 | 0 | 179 | 0 | 0
MARION | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 3 | 10
MARTINDALE | Drought management | 0 | 6 | 0 | 0 | 0 | 0 | 0
MARTINDALE WSC | CRWA Wells Ranch project Phase II (including Gonzales County) | 0 | 396 | 396 | 696 | 896 | 896 | 896
MARTINDALE WSC | Drought management | 0 | 9 | 0 | 0 | 0 | 0 | 0
MAXWELL WSC | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 400 | 800 | 1200 | 1600 | 2000
MAXWELL WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 11 | 55
MCCOY WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 5803000 | 0 | 807 | 807 | 807 | 807 | 1613
MCCOY WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 13 | 68 | 129
MINING, BEXAR | Industrial, steam-electric power generation, and mining water conservation | 0 | 0 | 0 | 921 | 1021 | 1123 | 1217
MINING, COMAL | Industrial, steam-electric power generation, and mining water conservation | 0 | 439 | 635 | 753 | 870 | 1068 | 1173
MINING, HAYS | Industrial, steam-electric power generation, and mining water conservation | 0 | 82 | 91 | 97 | 101 | 102 | 103
MOUNTAIN CITY | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 1385554 | 0 | 150 | 150 | 150 | 150 | 150 | Carrizo groundwater project | Other | Acquisition and Design Phase | Too soon | 15000 | 10500000 |  |  | Yes | 35690 | 400000000 | 2060 | Self (cash) | Yes | Mountain City has not contracted with the Hays Caldwell PUA for water supply.
MOUNTAIN CITY | Municipal water conservation | 0 | 1 | 3 | 6 | 10 | 16 | 22
MUSTANG RIDGE | Drought management | 0 | 6 | 0 | 0 | 0 | 0 | 0
MUSTANG RIDGE | GBRA mid basin (surface water) | 0 | 0 | 62 | 99 | 137 | 175 | 213
MUSTANG RIDGE | Municipal water conservation | 0 | 10 | 26 | 48 | 74 | 98 | 116
MUSTANG RIDGE | Purchase from wholesale water provider (GBRA) | 0 | 19 | 0 | 0 | 0 | 0 | 0
NATALIA | Drought management | 0 | 17 | 0 | 0 | 0 | 0 | 0
NATALIA | Edwards transfers | 0 | 194 | 238 | 279 | 314 | 349 | 383
NATALIA | Municipal water conservation | 0 | 24 | 31 | 38 | 46 | 58 | 73
NEW BRAUNFELS | Drought management | 0 | 525 | 0 | 0 | 0 | 0 | 0
NEW BRAUNFELS | GBRA Simsboro project (overdraft) | 0 | 0 | 907 | 4044 | 7151 | 10361 | 13920
NEW BRAUNFELS | Municipal water conservation | 0 | 815 | 1965 | 3632 | 5433 | 6650 | 8152
NIEDERWALD | Drought management | 0 | 7 | 0 | 0 | 0 | 0 | 0
NIEDERWALD | GBRA mid basin (surface water) | 0 | 0 | 118 | 183 | 244 | 317 | 377
NIEDERWALD | Municipal water conservation | 0 | 0 | 1 | 8 | 15 | 27 | 42
NIEDERWALD | Purchase from wholesale water provider (GBRA) | 0 | 58 | 0 | 0 | 0 | 0 | 0
NIXON | Municipal water conservation | 0 | 35 | 64 | 72 | 75 | 83 | 93
OAK HILLS WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 259000 | 0 | 0 | 0 | 0 | 0 | 323
OAK HILLS WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 26 | 76 | 136
OLMOS PARK | Municipal water conservation | 0 | 9 | 11 | 13 | 14 | 21 | 33
PEARSALL | Municipal water conservation | 0 | 116 | 223 | 272 | 271 | 294 | 324
PLEASANTON | Municipal water conservation | 0 | 156 | 300 | 448 | 523 | 565 | 615
PLUM CREEK WATER COMPANY | GBRA mid basin (surface water) | 0 | 0 | 0 | 0 | 195 | 454 | 657
PLUM CREEK WATER COMPANY | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 12 | 54
POINT COMFORT | Drought management | 0 | 11 | 0 | 0 | 0 | 0 | 0
POINT COMFORT | Municipal water conservation | 0 | 18 | 34 | 55 | 78 | 84 | 98
POINT COMFORT | Purchase from wholesale water provider (LNRA)/redistribution of supplies | 0 | 46 | 145 | 322 | 499 | 489 | 489
POLONIA WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 2087000 | 0 | 0 | 0 | 0 | 161 | 323
PORT LAVACA | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 30 | 89
PORT O'CONNOR MUD | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 4 | 11
POTEET | Municipal water conservation | 0 | 60 | 116 | 163 | 185 | 198 | 213
POTH | Municipal water conservation | 0 | 20 | 22 | 25 | 28 | 46 | 64
REFUGIO | Municipal water conservation | 0 | 44 | 94 | 100 | 114 | 130 | 144
RUNGE | Municipal water conservation | 0 | 15 | 22 | 24 | 26 | 31 | 37
SABINAL | Drought management | 0 | 20 | 0 | 0 | 0 | 0 | 0
SABINAL | Edwards transfers | 0 | 127 | 123 | 118 | 113 | 109 | 109
SABINAL | Municipal water conservation | 0 | 34 | 65 | 92 | 116 | 139 | 145
SAN ANTONIO | Drought management | 0 | 1233 | 0 | 0 | 0 | 0 | 0
SAN ANTONIO | Municipal water conservation | 0 | 5752 | 7318 | 8795 | 10490 | 15698 | 23711
SAN ANTONIO WATER SYSTEM | Aquifer storage and recovery project and phased expansion | 0 | 3800 | 16000 | 16000 | 16000 | 16000 | 16000 | [13 empty] | No | Not identified in the 2011 Plan as a WMS
SAN ANTONIO WATER SYSTEM | Brackish groundwater desalination (Wilcox Aquifer) | 236220000 | 0 | 12000 | 21000 | 26400 | 26400 | 26400 | Brackish groundwater development | Wells | Under Construction |  | 13,440 acft/yr | 80441792 | 411384326 | 2016 | Yes | 33600 |  | 2025 | TWDB | Yes | Phase 1 under construction
SAN ANTONIO WATER SYSTEM | Drought management | 0 | 37622 | 0 | 0 | 0 | 0 | 0 | Demand reduction | No Infrastructure | All Phases Fully Implemented | [10 empty] | Yes | Ongoing
SAN ANTONIO WATER SYSTEM | Edwards Aquifer recharge - Type 2 projects | 527643000 | 0 | 13451 | 13451 | 13451 | 13451 | 21577 | [13 empty] | No | No longer a planned project
SAN ANTONIO WATER SYSTEM | Edwards transfers | 0 | 35935 | 35935 | 35935 | 35935 | 35935 | 35935 |  |  | Currently Operating | [10 empty] | No | On going project
SAN ANTONIO WATER SYSTEM | Firm-up- run-of-river with off-channel reservoir - LCRA/SAWS project (Region L component) | 1986684000 | 0 | 0 | 90000 | 90000 | 90000 | 90000 | [13 empty] | No | Project terminated
SAN ANTONIO WATER SYSTEM | Recycled water programs | 168655703 | 15127 | 15127 | 15127 | 15127 | 15127 | 15127 | Recycled Water | Pipeline | Currently Operating | [10 empty] | Yes | Ongoing
SAN ANTONIO WATER SYSTEM | Regional Carrizo for SAWS (including Gonzalas County) | 136550000 | 0 | 11687 | 11687 | 11687 | 11687 | 11687 | Groundwater | Wells | All Phases Fully Implemented |  | 5300 | 149000000 |  | 2014 | No | 11688 |  | 2015 |  | Yes | Project constructed and online
SAN ANTONIO WATER SYSTEM | Seawater desalination | 1293827000 | 0 | 0 | 0 | 0 | 0 | 84012 | Seawater | Pipeline | Feasibility Study Ongoing | [5 empty] | No | 84012 | 1590590000 | 2050 | TWDB | Yes | Planned Project for 2050 decade
SAN MARCOS | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 110017629 | 0 | 0 | 1548 | 4953 | 8675 | 11910
SAN MARCOS | Municipal water conservation | 0 | 417 | 554 | 815 | 1282 | 1875 | 2656
SANTA CLARA | CRWA Wells Ranch project Phase II (including Gonzales County) | 0 | 100 | 0 | 0 | 0 | 0 | 0
SANTA CLARA | Drought management | 0 | 11 | 0 | 0 | 0 | 0 | 0
SANTA CLARA | GBRA mid basin (surface water) | 0 | 0 | 300 | 400 | 0 | 0 | 0
SANTA CLARA | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 0 | 0 | 500 | 700 | 900 | Carrizo groundwater project | Other | Acquisition and Design Phase | Too soon | 15000 | 10500000 |  |  | Yes | 35690 | 400000000 | 2060 | Self (cash) | Yes | Santa Clara has not contracted with the Hays Caldwell PUA for water supply.
SANTA CLARA | Municipal water conservation | 0 | 0 | 0 | 10 | 23 | 47 | 79
SCHERTZ | Municipal water conservation | 0 | 22 | 87 | 182 | 365 | 694 | 1088
SCHERTZ | Regional Carrizo for SSLGC project expansion (including Gonzales County) | 0 | 0 | 0 | 940 | 2425 | 4116 | 5924
SCHERTZ-SEGUIN LOCAL GOVERNMENT CORPORATION | Brackish groundwater desalination (Wilcox Aquifer) | 17374408 | 0 | 0 | 2000 | 2000 | 2000 | 2000
SCHERTZ-SEGUIN LOCAL GOVERNMENT CORPORATION | Regional Carrizo for SSLGC project expansion (including Gonzales County) | 28189000 | 0 | 10364 | 10364 | 10364 | 10364 | 10364
SEADRIFT | Municipal water conservation | 0 | 20 | 29 | 30 | 32 | 36 | 41
SEGUIN | Municipal water conservation | 0 | 377 | 853 | 1229 | 1448 | 1744 | 2131
SELMA | Municipal water conservation | 0 | 135 | 344 | 617 | 801 | 966 | 1122
SELMA | Regional Carrizo for SSLGC project expansion (including Gonzales County) | 0 | 0 | 316 | 762 | 757 | 748 | 749
SHAVANO PARK | Drought management | 0 | 41 | 0 | 0 | 0 | 0 | 0
SHAVANO PARK | Edwards transfers | 0 | 320 | 336 | 348 | 357 | 369 | 381
SHAVANO PARK | Municipal water conservation | 0 | 73 | 142 | 205 | 265 | 324 | 382
SOMERSET | Municipal water conservation | 0 | 29 | 70 | 110 | 131 | 152 | 177
SPRINGS HILL WSC | Brackish groundwater desalination (Wilcox Aquifer) | 13030806 | 0 | 0 | 0 | 0 | 0 | 1500 | Removed ourselves from this project |  |  | Dropped | 0
SPRINGS HILL WSC | Facilities expansion | 2277000 | 0 | 0 | 0 | 0 | 0 | 0 | New Elevated Storage | Storage facility | 0.1 |  | 0 | $20,000` | 3500000 | 2016 |  |  |  |  | Developers |  | Future development
SPRINGS HILL WSC | Municipal water conservation | 0 | 174 | 381 | 477 | 571 | 701 | 877 | Replaced Meters | Meter Replacement | 1 |  |  | $1.1 million |  | 2014 |  |  |  |  | TWDB Loan/Grant |  | Complete
SPRINGS HILL WSC | TWA Regional Carrizo (including Gonzales County) | 0 | 0 | 3000 | 6000 | 6000 | 6000 | 6000 | Dropped |  |  | Dropped | 0
SS WSC | Brackish groundwater desalination (Wilcox Aquifer) | 14357000 | 0 | 0 | 0 | 1120 | 1120 | 1120
SS WSC | Drought management | 0 | 78 | 0 | 0 | 0 | 0 | 0
SS WSC | Hays/Caldwell Public Utility Authority Project (including Gonzales County) | 0 | 0 | 0 | 0 | 0 | 0 | 690
SS WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 29537000 | 807 | 1613 | 1613 | 2420 | 3226 | 4033
SS WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 84 | 221
ST. HEDWIG | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 0 | 14
STEAM ELECTRIC POWER, ATASCOSA | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 4808000 | 807 | 807 | 807 | 807 | 807 | 1613
STEAM ELECTRIC POWER, VICTORIA | GBRA lower basin storage | 0 | 0 | 0 | 1865 | 1895 | 1927 | 1950
STEAM ELECTRIC POWER, VICTORIA | Purchase from wholesale water provider (GBRA) | 0 | 1791 | 1836 | 0 | 0 | 0 | 0
STOCKDALE | Municipal water conservation | 0 | 27 | 57 | 93 | 128 | 147 | 171
SUNKO WSC | Local groundwater Carrizo-Wilcox Aquifer (includes overdrafts) | 1375000 | 0 | 0 | 0 | 0 | 0 | 161
SUNKO WSC | Municipal water conservation | 0 | 3 | 6 | 10 | 29 | 54 | 92
TERRELL HILLS | Municipal water conservation | 0 | 14 | 18 | 21 | 24 | 39 | 65
TEXAS WATER ALLIANCE | TWA Regional Carrizo (including Gonzales County) | 313060000 | 0 | 27000 | 27000 | 27000 | 27000 | 27000
UNIVERSAL CITY | Drought management | 0 | 130 | 0 | 0 | 0 | 0 | 0
UNIVERSAL CITY | Edwards transfers | 0 | 113 | 421 | 680 | 630 | 606 | 606
UNIVERSAL CITY | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 49 | 148
UVALDE | Drought management | 0 | 304 | 0 | 0 | 0 | 0 | 0
UVALDE | Edwards transfers | 0 | 3172 | 3209 | 3229 | 3233 | 3235 | 3263
UVALDE | Municipal water conservation | 0 | 521 | 1017 | 1471 | 1882 | 2269 | 2652
VICTORIA | Municipal water conservation | 0 | 874 | 1597 | 1733 | 1844 | 2118 | 2485
WAELDER | Municipal water conservation | 0 | 0 | 0 | 0 | 3 | 7 | 11
WATER SERVICES INC | Drought management | 0 | 48 | 0 | 0 | 0 | 0 | 0
WATER SERVICES INC | Edwards transfers | 0 | 587 | 723 | 844 | 945 | 1031 | 1116
WATER SERVICES INC | Municipal water conservation | 0 | 0 | 0 | 0 | 18 | 50 | 105
WATER SERVICES INC | Purchase from wholesale water provider (SSLGC)/redistribution of supplies | 0 | 324 | 324 | 324 | 324 | 324 | 324
WATER SERVICES INC | TWA Regional Carrizo (including Gonzales County) | 0 | 0 | 1000 | 1000 | 1000 | 1000 | 1000
WIMBERLEY WSC | Drought management | 0 | 39 | 0 | 0 | 0 | 0 | 0
WIMBERLEY WSC | Municipal water conservation | 0 | 0 | 0 | 0 | 0 | 19 | 70
WIMBERLEY WSC | Wimberley and Woodcreek water supply project | 0 | 336 | 1425 | 1425 | 1425 | 1425 | 1425
WINDCREST | Edwards transfers | 0 | 235 | 235 | 235 | 235 | 235 | 235
WINDCREST | Municipal water conservation | 0 | 99 | 189 | 270 | 343 | 362 | 385
WOODCREEK | Drought management | 0 | 12 | 0 | 0 | 0 | 0 | 0
WOODCREEK | Municipal water conservation | 0 | 0 | 0 | 2 | 6 | 20 | 37
WOODCREEK | Wimberley and Woodcreek water supply project | 0 | 112 | 400 | 400 | 400 | 400 | 400
WOODCREEK UTILITIES INC | Municipal water conservation | 0 | 56 | 177 | 337 | 455 | 619 | 771
WOODCREEK UTILITIES INC | Wimberley and Woodcreek water supply project | 0 | 672 | 2655 | 2655 | 2655 | 2655 | 2655
WOODSBORO | Municipal water conservation | 0 | 5 | 6 | 7 | 8 | 14 | 20
YANCEY WSC | Edwards transfers | 0 | 214 | 395 | 562 | 710 | 851 | 985
YANCEY WSC | Municipal water conservation | 0 | 61 | 136 | 171 | 214 | 259 | 316
YOAKUM | Municipal water conservation | 0 | 14 | 16 | 17 | 18 | 20 | 27
YORKTOWN | Municipal water conservation | 0 | 0 | 2 | 2 | 2 | 5 | 13
Note on A1: HDR: Responses from Region L WUGs highlighted in green.

## DropDown (hidden)
Pipeline | Not Implemented | Too soon | 2011 | Yes | 2011 | Self (cash) | Yes
Canal | Sponsor Has Taken Official Action to Initiate Project | Financing | 2012 | No | 2012 | Local (market issue) | No
Water Treatment Plant | Feasibility Study Ongoing | Permit contraints | 2013 |  | 2013 | County
Impoundment | Permit Application Submitted/Pending | Environmental obstacles | 2014 |  | 2014 | TWDB
Wells | Acquisition and Design Phase | Other | 2015 |  | 2015 | State - Other
Other | Under Construction |  | 2016 |  | 2016 | Federal - EPA
No Infrastructure | Currently Operating |  |  |  | 2017 | Federal - USDA
| All Phases Fully Implemented |  |  |  | 2018 | Federal - Other
[5 empty] | 2019 | Other
[5 empty] | 2020 | Unknown
2025
2030
2035
2040
2045
2050
2060
2070